## Sheet1
System Development
DOCUMENT INFORMATION
Project Name | Prepared By |  | Period Start |  | Period End
AJJP Senior Project | J.W. Clark |  | 2010-11-08 |  | 2010-11-14
WEEKLY TASKS
Activity |  | Planned | Actual | Planned | Estimated | Status
|  | Start | Start | Finish | Finish
Publish project scope |  | 2010-11-09 | 2010-11-09 | 2010-11-12 | 2010-11-12 | complete
Publish project milestones |  | 2010-11-09 | 2010-11-16 | 2010-11-16 | 2010-11-16 | complete
User authentication system |  | 2010-11-16 | 2010-11-16 | 2010-11-30 | 2010-11-30 | started
Equipment Input/Output system |  | 2010-11-16 | 2010-11-16 | 2010-11-30 | 2010-11-30 | started
Database query system |  | 2010-11-16 | 2010-11-16 | 2010-11-30 | 2010-11-30 | started
Login page graphics & design |  | 2010-11-16 | 2010-11-16 | 2010-11-30 | 2010-11-30 | started
WEEKLY KEY DATES
Last Week's Accomplishments |  |  | Date Completed |  | Owner
Preliminary storyboard |  |  | 2010-11-08 |  | Aaron Baker
Preliminary database diagram |  |  | 2010-11-08 |  | Pat Martin
Significant Activities Next Week |  |  | Date Planned |  | Owner
Press release |  |  | 2010-11-23 |  | J.W. Clark
RISKS/DEPENDENCIES
Item |  | Probability | Impact
User authentication system |  | Low | The user authentication system is the first requirement for other systems to function correctly.
SQL Server database |  | Low | The database is the backbone of the system. Without it, the project will not complete.
CHANGE REQUEST
Description |  |  | Date Submitted |  | Date Approved
NEW ISSUES / ACTION ITEMS
Issue / Action Item |  | Impact |  |  | Assigned To | Due Date
File upload/download system |  | File storage and retrieval is a core component. The system will centralize project-specific documents. |  |  | J.W. Clark | 2010-11-23

## Sheet2
Milestones
| Start |  | Finish
Activity | Planned | Actual | Planned | Estimate | Status